## Corpvision
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
About Us | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Feature | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Servives | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-04 | 2022-01-05 | 100% | Đinh Công Trí
Progress | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-04 | 2022-01-05 | 100% | Đinh Công Trí
Testimonimal | 2022-01-06 | 2022-01-13 | 100% | Đinh Công Trí | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông
Blog | 2022-01-06 | 2022-01-13 | 100% | Đinh Công Trí | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông
Footer | 2022-01-06 | 2022-01-13 | 100% | Đinh Công Trí | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Minh Nguyên Phú

## Studious
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Banner | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Feature | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Course | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Servives | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Number | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Testimonimal | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Team | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
About | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
Footer | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Trần Đông

## Pooch Care
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header + Carousel | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
About | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Feauture | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Service | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Number | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Pricing Plan | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Video Popup | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Testimonial | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Subscribe | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Footer | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Trần Đông

## Dinner
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Banner | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Content 1 | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Agent-block | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Popular catergories | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Minh Nguyên Phú | 2021-12-25 | 2021-12-26 | 100% | Đinh Công Trí
Home-services | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Deliciousness | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Video popup | 2021-12-27 | 2022-01-03 | 100% | Đinh Công Trí | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Trần Đông
Blog post | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
Testimonial | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
Footer | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Trần Đông | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Trần Đông

## Farmstead
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Grow Naturally | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Servive | 2021-12-17 | 2021-12-24 | 100% | Nguyễn Trần Đông | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Minh Nguyên Phú
Why chose us | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-04 | 2022-01-05 | 100% | Đinh Công Trí
Homepage Service | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-04 | 2022-01-05 | 100% | Đinh Công Trí
Products | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-04 | 2022-01-05 | 100% | Đinh Công Trí
Testimonimal | 2022-01-06 | 2022-01-13 | 100% | Đinh Công Trí | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông
Footer | 2022-01-06 | 2022-01-13 | 100% | Đinh Công Trí | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Trần Đông

## Masterwork
Tasks Name: | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header + Banner | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Trần Đông
Tool | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Trần Đông
About | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Trần Đông
Number | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Trần Đông
Blog | 2021-12-17 | 2021-12-24 | 100% | Đinh Công Trí | 2021-12-25 | 2021-12-26 | 100% | Nguyễn Trần Đông
Solution | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Minh Nguyên Phú
FAQ | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Minh Nguyên Phú
Project | 2021-12-27 | 2022-01-03 | 100% | Nguyễn Trần Đông | 2022-01-04 | 2022-01-05 | 100% | Nguyễn Minh Nguyên Phú
Testimonial | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Community | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Footer | 2022-01-06 | 2022-01-13 | 100% | Nguyễn Minh Nguyên Phú | 2022-01-14 | 2022-01-15 | 100% | Đinh Công Trí
Dark Mode | 2022-01-14 | 2022-01-15 | 100% | Nguyễn Trần Đông | 2022-01-15 | 2022-01-16 | 100% | Nguyễn Minh Nguyên Phú